## Sheet1
Task Name | Start Date | End Date | Category | Resource | Progress | Priority
Project Kickoff | 2024-03-01 | 2024-03-03 | Planning | Project Manager | 100 | High
Research Phase | 2024-03-04 | 2024-03-10 | Research | Research Team | 100 | High
UI/UX Design | 2024-03-11 | 2024-03-17 | Design | Design Team | 90 | High
Frontend Development | 2024-03-18 | 2024-03-31 | Development | Frontend Team | 75 | High
Backend Development | 2024-03-18 | 2024-03-31 | Development | Backend Team | 80 | High
Database Integration | 2024-04-01 | 2024-04-07 | Development | Backend Team | 60 | Medium
Testing | 2024-04-08 | 2024-04-14 | Testing | QA Team | 40 | High
Deployment | 2024-04-15 | 2024-04-17 | Deployment | DevOps Team | 0 | Critical